## Sheet1
Task | Responsible entity | Responsible person | Failure Modes | Mitigation
Candidate downloads and sends application from website | Candidate | Candidate | Website fails or candidate cannot work with documents | Put Sara's e-mail to contact if failure; Sara sends forms
Confirmation of receipt of general application sent to candidate | Membership Committee | Reyna | Application gmail fails to forward applications | Reyna will check gmail account daily; Misty, Sara and Marshall have access to account and can check in her absence
Pick up Background Check Form from PO Box | Secretary | Jay | Background check form gets lost in mail | Jay sends e-mail to candidate after 5 days if background check form fails to appear
Confirmation of receipt of background check form sent to candidate | Secretary | Jay
Submit Background check request to County | Secretary | Jay
Background check completed | County | County | County fails to do background check | Jay follows up after 10 working days following submission
Reference checks initiated | Membership Committee | Jerry takes first ref; Marshall takes second; Reyna takes third
Reference checks completed | Membership Committee | Jerry | Unable to contact all references | Make 3 attempts to contact. Accept 2 out of 3. If only 1, contact candidate for help.
Set interview date and invite candidate | Membership Committee | Jerry | Candidate fails to shows up for interview | If no acceptable excuse, fail candidate; if good excuse, reschedue
Interview candidate | Membership Committee | Jerry, Marshall, Reyna
Candidate voted in | Membership Committee | Jerry
Mentor assigned; mentor entered into Accepted Candidate Packet document | SAR Coordinator; Secretary | Misty; Jay
Accepted Candidate Packet and medical form provided to candidate | Secretary | Jay
Candidate contact information provided to Web Master, SAR Coordinator, Training Officer, Mentor | Secretary | Jay
Member added to GroupMe and given access to training google drive | SAR Coordinator | Misty
Member given access to 1st aid google drive | Medical Officer | Max
Membership application archived | Secretary | Jay | Forms missing | Write memo to file to say form was created by could not be found
General Application
Background check consent
Background check results
3 Reference Interview Forms
Candidate Interview Form
Copy of candidate's membership packet
Medical form put in response and event trailers | SAR Coordinator; President | Misty; Jerry